## Sheet1
Jack In The Bot FIRST Team 2910 Build Season ¦ Competition Season Schedule
Color Legend | Saturday and Mid-Winter Holiday | Day Off Sunday | Important Due Date | Parent Meetings
Weekday Meeting Times 6pm-9pm
Saturday and Mid-Winter Break Meeting Times During Build 9am-5pm
Saturday Meeting Times After Build 9am-noon
Date | time axis 2013-01-05 to 2013-04-01
Engineering Build Tasks | bar: 2013-01-05 to 2013-01-12; 2013-01-14 to 2013-01-19; 2013-01-21 to 2013-01-26; 2013-01-28 to 2013-02-02; 2013-02-04 to 2013-02-09; 2013-02-11 to 2013-02-23; 2013-02-25 to 2013-03-02; 2013-03-04 to 2013-03-09; 2013-03-11 to 2013-03-16; 2013-03-18 to 2013-03-23; 2013-03-25 to 2013-03-30; 2013-04-01
Kickoff | 2013-01-05: 6am - 1pm
Game Rule Review | 2013-01-05: 1pm - 6pm
Sub-Team Rule Review ¦ Presentation | 2013-01-06: JHS 9am-Noon
Game Strategy - Human Simulation | 2013-01-06: 1pm-4pm Glacier Peak HS
Game Strategy - Development | 2013-01-07: 6pm - 9pm
Robot's Key Performance Factors Defined | 2013-01-08: 6pm - 9pm
Conceptual Design sub-team meetings | 2013-01-08: 6pm - 9pm; 2013-01-09: 6pm-8pm
Conceptual Design Review | 2013-01-09: 8pm - 9pm
Select Design Concept | 2013-01-10: 6pm-7pm
Determine Sub System Requirements | 2013-01-10: 7pm-8pm
Determine Sub System Teams | 2013-01-10: 8pm-9pm
Sub-System Prelim Designs | 2013-01-10: Get started; 2013-01-14: finish
Sub-System Reviews | 2013-01-14: Begin; 2013-01-15: Finish Reviews
Drive Train Fabrication | 2013-01-15: Begin; 2013-01-22: Complete Drive Train
Manipulator Fabrication | 2013-01-15: Begin; 2013-01-31: Complete Manipulator
Transport Fabrication | 2013-01-15: Begin; 2013-01-31: Complete Transport
Electrical Fabrication | 2013-01-15: Begin; 2013-02-02: Complete Electrical
Sub-System Integration | 2013-01-22: Begin; 2013-02-07: Complete
Robot Integration Test | 2013-02-07: Begin; 2013-02-11: Complete
Test/Improve Hardware/Software | 2013-02-11: Begin; 2013-02-14: Complete
Software Development
Determine Hardware/Software Interfaces | 2013-01-10: Begin; 2013-01-12: Finish
Determine Software Architechure | 2013-01-12: Begin; 2013-01-14: Finish
Develop Protype Code | 2013-01-14: Begin; 2013-01-21: Finish
Test Protype Code on Test Bench | 2013-01-21: Begin; 2013-01-23: Finish
Integrate Drive Train Software | 2013-01-23: Begin; 2013-01-26: Finish
Write code for Robot | 2013-01-26: Begin; 2013-02-02: Complete
Integrate / debug Software on Robot | 2013-02-02: Begin; 2013-02-05: Complete
Bag and Tag Robot | 2013-02-19: Bag and Tag
Important Dates
FLL State Competition Hosted By Jack In The Bot at JHS Posters Feb 2 Setup Feb 9 Competition Feb 10 | 2013-02-02: Posters due; 2013-02-09: Setup for State; 2013-02-11: 5:30 am - 8:30pm
Central Washington Regional (March 21 - 23) | 2013-03-21: 4:30 am departure; 2013-03-23: 9pm return
Seattle Regional Competition (March 28-30) | 2013-03-28: 6am departure; 2013-03-30: 7pm return
FIRST Robotics World Championships St. Louis (April 23-28)
Everett Public Schools Tech Fair (Jan 23) | 2013-01-23: 4:30pm - 8:30pm
PTSA Presentation (March 6) | 2013-03-06: PTSA Presentation
Date | time axis 2013-01-05 to 2013-04-01
Non Engineering Build Season Tasks | bar: 2013-01-05 to 2013-01-12; 2013-01-14 to 2013-01-19; 2013-01-21 to 2013-01-26; 2013-01-28 to 2013-02-02; 2013-02-04 to 2013-02-09; 2013-02-11 to 2013-02-23; 2013-02-25 to 2013-03-02; 2013-03-04 to 2013-03-09; 2013-03-11 to 2013-03-16; 2013-03-18 to 2013-03-23; 2013-03-25 to 2013-03-30; 2013-04-01
Chairman's Essay 1st Draft Jan 18 2nd Draft Feb. 1 Final Draft Feb. 12 Present to Team Feb. 16 Submit Feb 19 | 2013-01-12: Back to Sub Team; 2013-01-18: 1st Draft Due; 2013-01-19: Return Draft; 2013-02-01: 2nd Draft Due; 2013-02-02: 2nd Draft returned; 2013-02-12: Final Draft; 2013-02-16: Final Draft - Present to Team; 2013-02-19: submit to TIMS; 2013-02-21: 8am Deadline
Chairman's Presentation 1st Draft 2nd Draft Submit March 6
Chairman's Video Storyboard TBD Present to Team/Parents March 6 Formal Presentation TBD
Documentation Binders Final Event write-ups complete Jan 13 Add Pictures to binder Jan 20 Document Binder Update Complete Jan 27 | 2013-01-13: Event write-ups complete; 2013-01-27: Document Binder update complete; 2013-02-23: Documentation Binder Completed
Engineering Binder Update weekly due each Saturday Binder Complete Feb 23 | 2013-01-12: Update CAD Drawing & Design Information; 2013-01-19: Update CAD Drawing & Design Information; 2013-01-26: Update CAD Drawing & Design Information; 2013-02-02: Update CAD Drawing & Design Information; 2013-02-09: Update CAD Drawing & Design Information; 2013-02-16: Update CAD Drawing & Design Information; 2013-02-23: Engineering Binder Completed
Pit Design Preliminary Design Jan 20 Design Finalized Feb 9 Parts Ordered Feb 14 Pit Complete Fab 24 | 2013-02-09: Decisions Finalized; 2013-02-14: Pit parts ordered
PR - Articles Contact Newspapers Jan 12 Send FLL article to newspapers Feb 2 Send FRC article to newspapers March 10 | 2013-01-12: Contact Newspapers about the team's interest in publishing 2 articles; 2013-02-02: Send to Newspaper promotion about the FLL Competition; 2013-03-10: Send to Newspaper promoting FRC Competitions
Safety Binder Revise MSDS Jan 12 Update MSDS Jan 19 | 2013-01-12: Update MSDS sheets; 2013-01-19: Update MSDS sheets if needed
Custom Spirit Gear Draft Button Design Feb 14 Final Button Design Feb 23 JITB Journey Video Practice March 2 JITB Journey Video complete March 9 Spirit Signs complete March 16 | 2013-02-14: Draft button design due; 2013-02-23: Final button design; 2013-03-16: Signs complete
Spirit Gear Selection and Ordering Decisions Finalized Jan 19 Order Gear Jan 26 | 2013-01-19: Decisions Finalized; 2013-01-26: Spirit Gear Ordered Deadline
Game Strategy / Competition Scouting Draft Scouting Form Feb 23 Finalized Scouting Form March 9 | 2013-02-23: Draft Scouting Form due; 2013-03-09: Finalized Scouting Form due
Sub Team Binders Update weekly due each Saturday Binders Finalized for Competition Feb 23 Pictures put in hard drive - Interesting Quotes - Weekly Goals - Bill Of Materials (Receipts Collected)- Accomplishment Summary/Story | 2013-01-12: Update Sub-Team Binders; 2013-01-19: Update Sub-Team Binders; 2013-01-26: Update Sub-Team Binders; 2013-02-02: Update Sub-Team Binders; 2013-02-09: Update Sub-Team Binders; 2013-02-16: Update Sub-Team Binders; 2013-02-23: All diagrams added - Cleaned Up and Ready for competition
Thank You Letter / Invitation to Sponsors, Politicians, School District Personnel Draft Complete Jan 12 Send Letters Feb 4 Video for Invite Complete Jan 26 | 2013-01-12: Begin Draft; 2013-01-22: Due; 2013-02-04: Send Letters
Team Meetings Resume on Mondays starting (April 8) | 2013-02-25: Regular Team Meeting Build Highlights 5pm-7pm
Parent Meetings Build Season Info Jan 14 at 7:00pm Competition Info Feb 25 at 7:00pm Planning Mtg for World Championships April 1 at 7:00pm (Tentative) | 2013-01-14: Build Season Information Meeting 7pm Library; 2013-02-25: Parent Competition Meeting 7pm Library; 2013-04-01: Planning Meeting for World Championship (Tentative)